## 55T-1
Infra resources permit delay data MIS
Vendor Name:- Month:- |  | IHPL | Month-July-2026
S. NO. | Date | Department | Location | User Name | Jobs nature SD/N/MSD | Crane reaching time at site | Crane shift reporting time (A/G/B/C shift) | Crane Type |  | Permit No. | PERMIT PROCESS STEPS (Railway time format) | [6 empty] | Actual reason of permit delay
[9 empty] | Hiring cost/ hour |  | A. Permit Create Time (Created by User) | B. PTW requested time (User requested to Operation) | C. Permit Issued time (Operation approved permit) | D. Permit Taken time (Vendor accepted) | Total permit delay time (D-A) | Total permit delay hours | Permit delay cost |  | BD | G | 40T | 1350
1 | 2026-07-01 | BELT GROUP | SP HIGH LINE | ANKUR GUPTA |  | 9:30:00AM | G |  |  | 110022250683 | 10:25 | 10:46 | 10:46 | 10:52
2 | 2026-07-02 | SP-1 |  | VIKASH DAS |  | 9:30:00AM | G |  |  | 110022271173 | 11:02:00AM | 11:30:00AM | 11:30:00AM | 11:30:00AM
3 | 2026-07-04 | F-BF | INBA | ABHISHEK SHARMA |  | 9:30:00AM | G |  |  | 110022308067 | 9:47:00AM | 9:59:00AM | 9:59:00AM | 10:09:00AM
4 | 2026-07-05 | F-BF | INBA | ABHISHEK SHARMA |  | 8:30:00AM | G |  |  | 110022321438 | 9:00:00AM | 9:08:00AM | 9:08:00AM | 9:14:00AM
5 | 2026-07-06 | F-BF | INBA | ABHISHEK SHARMA |  | 8:30:00AM | G |  |  | 110022338355 | 9:42:00AM | 10:44:00AM | 3:05:00AM | 3:41:00AM
6 | 2026-07-08 | F-BF | INBA | ABHISHEK SHARMA |  | 8:30:00AM | G |  |  | 110022380412 | 10:38 | 10:53 | 11:36 | 11:36
7 | 2026-07-09 | TSCR | MILL | SANDEEP VISHWAKARMA |  | 9:30:00AM | G |  |  | 110022400749 | 10:40 | 12:36 | 12:36 | 13:52
8 | 2026-07-10 | RMM | COAL YARD | SOURAV SHARMA |  | 8:30:00AM | G |  |  | 110022421859 | 11:40 | 14:13 | 14:16 | 15:15
9 | 2026-07-11 | RMM | COAL YARD | SOURAV SINHA |  | 8:30:00AM | G |  |  | 110022431436 | 8:55 | 9:00 | 9:06 | 9:51
10 | 2026-07-12 | PP |  | ANUJ MISHRA |  | 9:30:00AM | G |  |  | 110022431478 | 10:26:00AM | 10:30 | 10:31 | 10:37
11 | 2026-07-13 | RMM |  | RAJNISH SINGH |  | 9:30:00AM | G |  |  | 110022474071 | 10:01 | 11:29 | 11:29 | 11:30
12 | 2026-07-14 | NBM |  | A N BAHERA |  | 9:30:00AM | G |  |  | 110022498843 | 14:21 | 14:30 | 14:31 | 14:31
13 | 2026-07-15 | F-BF |  | ABHISHEK SHARMA |  | 9:00:00AM | G |  |  | 110022514924 | 9:48 | 10:16 | 10:48 | 11:31:00AM
14 | 2026-07-16 | NBM |  | A N BAHERA |  | 9:00:00AM | G |  |  | 110022533228 | 9:15:00AM | 9:29:00AM | 9:30:00AM | 9:30:00AM
15 | 2026-07-17 | LD-2 FME |  | RITAM SAMANTA |  | 9:30:00AM | G |  |  | 110022551633 | 9:15:00AM | 9:34 | 9:35 | 9:36:00AM
16 | 2026-07-18 | BELT GROUP | COKE PLANT BATTERY 10 & 11 | RAJNISH SINGH |  | 9:30:00AM | G |  |  | 110022575496 | 10:24 | 10:33 | 10:48 | 10:49
17 | 2026-07-19 | COKE PLANT | NEW BPP | SHASHIKANT SINGH |  | 9:00:00AM | G |  |  | 110022588102 | 8:45 | 8:55:00AM | 8:58 | 9:02:00AM
18 | 2026-07-21 | HSM-FME |  | SUMIT KUMAR |  | 9:00:00AM | G |  |  | 110022624413 | 9:05 | 10:05 | 10:05 | 10:30
19 | 2026-07-22 | HSM-FME |  | SUMIT KUMAR |  | 9:00:00AM | G |  |  | 110022646607 | 9:21:00AM | 9:30 | 9:30 | 9:32
20 | 2026-07-23 | BOT PLANT |  | JAYANAND KUMAR |  | 9:00:00AM | G |  |  | 110022665747 | 9:03:00AM | 10:02:00AM | 10:03:00AM | 10:38
21 | 2026-07-25 | BOT PLANT |  | JAYANAND KUMAR |  | 9:00:00AM | G |  |  | 110022706520 | 9:02 | 9:36 | 9:39 | 9:45
22 | 2026-07-26 | PP |  | PANCHANAN PANDA |  | 9:00:00AM | G |  |  | 110022722041 | 9:08:00AM | 9:10:00AM | 9:10:00AM | 10:05:00AM
23 | 2026-07-29 | COKE PLANT |  | KULDEEP SURIN |  | 9:30:00AM | G |  |  | 110022781423 | 9:40 | 9:58:00AM | 9:58:00AM | 10:01:00AM
24 | 2026-07-30 | PP | GAS BOOSTER | BANWARI ORAON |  | 9:00:00AM | G |  |  | 110022768585 | 10:04:00AM | 10:55:00AM | 11:13:00AM | 11:21:00AM
25 | 2026-07-31 | PP | GAS BOOSTER | BANWARI ORAON |  | 9:00:00AM | G |  |  | 110022820315 | 9:29:00AM | 10:57:00AM | 11:03:00AM | 11:10:00AM

## 55T-2
Infra resources permit delay data MIS
Vendor Name:- Month:-
S. NO. | Date | Department | Location | User Name | Jobs nature SD/N/MSD | Crane reaching time at site | Crane shift reporting time (A/G/B/C shift) | Crane Type |  | Permit No. | PERMIT PROCESS STEPS (Railway time format) | [6 empty] | Actual reason of permit delay
[9 empty] | Hiring cost/ hour |  | A. Permit Create Time (Created by User) | B. PTW requested time (User requested to Operation) | C. Permit Issued time (Operation approved permit) | D. Permit Taken time (Vendor accepted) | Total permit delay time (D-A) | Total permit delay hours | Permit delay cost |  | BD | G | 40T | 1350
1 | 2026-07-01 | COKE PLANT |  | JAYANAND KUMAR |  | 9:00 | G |  |  | 110022247528 | 9:21:00AM | 9:32:00AM | 9:39:00AM | 9:42:00AM
2 | 2026-07-02 | RMBB-1 | BLENDING PLANT | MANISHA KUMARI |  | 9:00 | G |  |  | 110022267275 | 9:20 | 10:05 | 10:05 | 10:05
3 | 2026-07-04 | F-BF |  | ABHISHEK SHARMA |  | 9:30 | G |  |  | 110022309937 | 10:52:00AM | 11:08:00AM | 11:09:00AM | 11:00
4 | 2026-07-05 | F-BF |  | ABHISHEK SHARMA |  | 9:00 | G |  |  | 110022322165 | 9:25 | 10:58 | 10:58 | 10:59
5 | 2026-07-06 | BELT GROUP |  | CHANDRA KANTA |  | 9:00 | G |  |  | 110022335235 | 9:00 | 11:05 | 11:06 | 11:06
6 | 2026-07-07 | RMM |  | SOURAV SHARMA |  | 9:30 | G |  |  | 110022361433 | 11:56 | 14:21 | 14:21 | 14:29
7 | 2026-07-08 | PP |  | SATYENDRA KUMAR |  | 8:30 | G |  |  | 110022370164 | 8:45 | 10:08 | 10:09 | 10:28
8 | 2026-07-09 | FMD |  | P.R JENA |  | 9:00 | G |  |  | 110022379640 | 9:01 | 11:38 | 11:38 | 11:53
9 | 2026-07-10 | FMD |  | P.R JENA |  | 8:30 | G |  |  | 110022415302 | 8:50 | 11:55 | 11:56 | 11:59
10 | 2026-07-11 | FMD |  | P.R JENA |  | 8:30 | G |  |  | 110022433429 | 8:45 | 10:09 | 10:09 | 10:55
11 | 2026-07-12 | ES |  | KAUSHAL KISHORE |  | 9:00 | G |  |  | 110022453958 | 9:25 | 10:58 | 11:02 | 11:06
12 | 2026-07-13 | IBF |  | ANKIT SHRIVASTAV |  | 9:00 | G |  |  | 110022476160 | 11:49 | 12:03 | 12:03 | 12:42
13 | 2026-07-14 | BELT GROUP |  | RAJNISH SINGH |  | 9:00 | G |  |  | 110022495254 | 10:02:00AM | 12:11 | 12:11 | 12:11
14 | 2026-07-17 | HSM |  | SANJEEV ODHAR |  | 9:00 | G |  |  | 110022556070 | 10:53 | 11:25 | 11:28 | 11:33:00AM
15 | 2026-07-19 | LD-2 FME | NEAR FP CANTEEN | RITAM SAMANTA |  | 9:00 | G |  |  | 110022589627 | 9:39 | 9:48:00AM | 948:00AM | 9:48:00AM
16 | 2026-07-21 | RMM | RMBB-1 | SANDEEP SINHA |  | 9:00 | G |  |  | 110022617366 | 10:12 | 11:06 | 11:07 | 11:26
17 | 2026-07-22 | PP | BELT GROUP | RAJNISH SINGH |  | 9:00 | G |  |  | 110022643638 | 10:09 | 10:21 | 10:22 | 10:39
18 | 2026-07-23 | LD-2 |  | RITAM SAMANTA |  | 9:00 | G |  |  | 110022665456 | 9:00 | 9:45 | 9:45 | 9:45
19 | 2026-07-24 | BOT PLANT |  | JAYANAND KUMAR |  | 8:30 | G |  |  | 110022686145 | 8:52 | 9:27 | 9:33 | 9:39
20 | 2026-07-25 | LP |  | KUNDAN JHA |  | 9:30 | G |  |  | 11002270617 | 9:37 | 10:11:00AM | 10:11:00AM | 10:19:00AM
21 | 2026-07-26 | A-F BF |  | KUSHAGRA KUMAR |  | 9:00 | G |  |  | 110022723373 | 9:05:00AM | 9:44:00AM | 9:44:00AM | 9:44
22 | 2026-07-27 | PP |  | PANCHANAN PANDA |  | 9:00 | G |  |  | 110022736817 | 9:10:00AM | 10:13:00AM | 10:13:00AM | 10:16:00AM
23 | 2026-07-28 | FMD |  | KADMA RAGHU |  | 8:30 | G |  |  | 110022757405 | 8:57:00AM | 9:12:00AM | 9:13:00AM | 9:45:00AM
|  | PP |  | PANCHANAN PANDA |  | 12:00:00PM |  |  |  | 110022764401 | 12:12:00PM | 12:14:00PM | 12:21:00PM | 2:54:00PM
24 | 2026-07-29 | RMM |  | RATAN MAHATO |  | 9:30 | G |  |  | 110022775470 | 9:35:00AM | 10:32:00AM | 10:33:00AM | 10:33:00AM
25 | 2026-07-30 | BIM |  | RAJESH NAYAK |  | 9:30 | G |  |  | 110022803823 | 10:02:00AM | 10:16:00AM | 10:20:00AM | 10:21
26 | 2026-07-31 | FMD |  | SLOK VERMA |  | 9:00 | G |  |  | 110022817588 | 9:22:00AM | 9:38:00AM | 9:39:00AM | 10:08:00AM

## SANY-110T
Infra resources permit delay data MIS
Vendor Name:- Month:-
S. NO. | Date | Department | Location | User Name | Jobs nature SD/N/MSD | Crane reaching time at site | Crane shift reporting time (A/G/B/C shift) | Crane Type |  | Permit No. | PERMIT PROCESS STEPS (Railway time format) | [6 empty] | Actual reason of permit delay
[9 empty] | Hiring cost/ hour |  | A. Permit Create Time (Created by User) | B. PTW requested time (User requested to Operation) | C. Permit Issued time (Operation approved permit) | D. Permit Taken time (Vendor accepted) | Total permit delay time (D-A) | Total permit delay hours | Permit delay cost |  | BD | G | 40T | 1350
1 | 2026-07-01 | SP-2 | BARREL AREA | D MAWAL |  | 9:00 | G |  |  | 110022249125 | 9:47 | 10:03 | 10:16 | 10:17
2 | 2026-07-02 | SP-2 | BARREL AREA | D MAWAL |  | 8:30 | G |  |  | 110022264667 | 8:43 | 8:58 | 9:04 | 9:10
3 | 2026-07-03 | SP-2 | BARREL AREA | D MAWAL |  | 8:30 | A |  |  | 110022283420 | 7:14 | 7:50 | 7:50 | 7:51
4 | 2026-07-04 | SP-2 | BARREL AREA | D MAWAL |  | 8:30 | G |  |  | 110022305872 | 9:11 | 9:30 | 9:37 | 9:38
5 | 2026-07-06 | SP-2 | BARREL AREA | SUJOY MUKHERJEE |  | 8:30 | G |  |  | 110022338086 | 9:35 | 10:10 | 10:26 | 10:27
6 | 2026-07-07 | CP | BATTERY 10&11 | K C PRUSTY |  | 9:00 | G |  |  | 110022356511 | 9:11 | 9:45 | 9:45 | 9:51
7 | 2026-07-08 | CP | BATTERY 10&11 | SANJAY MISHRA |  | 9:00 | G |  |  | 110022377431 | 9:29 | 9:39 | 9:39 | 9:41
8 | 2026-07-13 | TSG | SINTER MACHINE ROUTE | PARMENDRA KUMAR |  | 9:00 | G |  |  | 110022474822 | 10:24 | 10:51 | 10:51 | 10:53
9 | 2026-07-14 | TSG | SINTER MACHINE ROUTE | PARMENDRA KUMAR |  | 9:00 | G |  |  | 110022495776 | 10:17 | 10:23 | 10:23 | 10:25
10 | 2026-07-15 | F-BF |  | ABHISHEK SHARMA |  | 9:00 | G |  |  | 110022515094 | 9:51 | 10:16 | 10:49 | 11:01
11 | 2026-07-17 | BELT GROUP | PELLET SCREENING | RAJNISH SINGH |  | 9:30 | G |  |  | 110022550141 | 10:40 | 10:56 | 10:57:00AM | 11:04:00AM
12 | 2026-07-18 | LD-2 |  | SOUMITRA BID |  | 9:30 | G |  |  | 110022576600 | 11:52 | 11:56 | 11:56 | 11:56
13 | 2026-07-19 | COKE PLANT | NEW BPP | SHASHIKANT SINGH |  | 8:30 | G |  |  | 110022588066 | 8:42 | 9:20 | 9:20 | 9:26
14 | 2026-07-20 | BG |  | RAJNISH SINGH |  | 9:00 | G |  |  | 110022590494 | 15:51 | 15:58 | 15:59 | 16:07
15 | 2026-07-22 | BELT GROUP |  | RAJNISH SINGH |  | 9:00 | G |  |  | 110022648623 | 9:48:00AM | 11:07 | 11:26 | 11:26
16 | 2026-07-24 | BOT PLANT |  | SHIVANSH MISHRA |  | 9:00 | G |  |  | 110022686883 | 9:05:00AM | 9:42:00AM | 9:42:00AM | 9:45:00AM
17 | 2026-07-25 | CP |  | SHIVANSH MISHRA |  | 9:00 | G |  |  | 110022706940 | 9:07:00AM | 9:34:00AM | 10:00:00AM | 10:00:00AM
18 | 2026-07-28 | SP-1 |  | SURENDRA KUMAR |  | 9:30 | G |  |  | 110022762119 | 9:56 | 11:12 | 11:12 | 11:12
19 | 2026-07-29 | SP-1 |  | SURENDRA KUMAR |  | 8:30 | G |  |  | 110022778478 | 8:59 | 10:07 | 10:07 | 10:08
20 | 2026-07-30 | PP | DRIER#2 | ROHIT KUMAR |  | 8:30 | G |  |  | 110022798424 | 8:49 | 9:27 | 9:27 | 9:42

## XCMG-110 T-1112
Infra resources permit delay data MIS
Vendor Name:- Month:-
S. NO. | Date | Department | Location | User Name | Jobs nature SD/N/MSD | Crane reaching time at site | Crane shift reporting time (A/G/B/C shift) | Crane Type |  | Permit No. | PERMIT PROCESS STEPS (Railway time format) | [6 empty] | Actual reason of permit delay
[9 empty] | Hiring cost/ hour |  | A. Permit Create Time (Created by User) | B. PTW requested time (User requested to Operation) | C. Permit Issued time (Operation approved permit) | D. Permit Taken time (Vendor accepted) | Total permit delay time (D-A) | Total permit delay hours | Permit delay cost |  | BD | G | 40T | 1350
1 | 2026-07-01 | TSCR | FINISHING MILL | ANIL KUMAR |  | 9:30 | G |  |  | 110022250390 | 10:15 | 10:40 | 10:40 | 10:43
2 | 2026-07-02 | TSCR | FINISHING MILL | ANIL KUMAR |  | 9:30 | G |  |  | 110022265940 | 10:09 | 10:23 | 11:04 | 11:04
3 | 2026-07-03 | TSCR | FINISHING MILL | ANIL KUMAR |  | 6:30 | A |  |  | 110022274626 | 7:27 | 7:29 | 7:49 | 7:49
4 | 2026-07-06 | FMD |  | SAYAN HAZRA |  | 9:30 | G |  |  | 110022334887 | 10:40:00AM | 12:08 | 12:08 | 12:10
5 | 2026-07-07 | CP-IEM |  | SURAJ BOTHARA |  | 9:00 | G |  |  | 110022356511 | 9:12 | 9:45 | 9:51 | 9:54
6 | 2026-07-08 | RMM |  | SOURAV SHARMA |  | 14:00 | B |  |  | 110022378329 | 14:24 | 14:53 | 3:02 | 3:41
7 | 2026-07-11 | TSG |  | PARMENDRA KUMAR |  | 8:30 | G |  |  | 110022450138 | 10:57 | 11:08 | 11:14 | 11:14
8 | 2026-07-12 | TSG |  | PARMENDRA KUMAR |  | 8:30 | G |  |  | 110022456348 | 10:19 | 10:27:00AM | 10:30:00AM | 10:30:00AM
9 | 2026-07-13 | TSG |  | PARMENDRA KUMAR |  | 8:30 | G |  |  | 110022471016 | 9:12:00AM | 9:26:00AM | 9:32:00AM | 9:32:00AM
10 | 2026-07-15 | TSG |  | PARMENDRA KUMAR |  | 8:30 | G |  |  | 110022517729 | 11:45:00AM | 12:20:00PM | 12:43:00PM | 1:08:00PM
11 | 2026-07-17 | TSG |  | PARMENDRA KUMAR |  | 8:30 | G |  |  | 110022558560 | 14:23 | 2:49:00PM | 2:50:00PM | 2:50:00PM
12 | 2026-07-18 | TSG |  | PARMENDRA KUMAR |  | 8:30 | G |  |  | 110022575907 | 10:45:00AM | 11:01:00AM | 11:06:00AM | 12:06:00PM
13 | 2026-07-19 | TSG |  | PARMENDRA KUMAR |  | 8:30 | G |  |  | 110022589736 | 9:43 | 10:08:00AM | 10:08:00AM | 10:08:00AM
14 | 2026-07-20 | TSG |  | PARMENDRA KUMAR |  | 8:30 | G |  |  | 110022608671 | 10:23:00AM | 11:04:00AM | 11:04:00AM | 11:05:00AM
15 | 2026-07-21 | TSG |  | PARMENDRA KUMAR |  | 8:30 | G |  |  | 110022634393 | 16:14 | 4:37:00PM | 5:59:00PM | 5:59:00PM
16 | 2026-07-22 | TSG |  | PARMENDRA KUMAR |  | 8:30 | G |  |  | 110022650648 | 11:02:00AM | 11:34:00AM | 11:34:00AM | 11:40:00AM
17 | 2026-07-23 | TSG |  | PARMENDRA KUMAR |  | 8:30 | G |  |  | 110022667282 | 9:24 | 9:33 | 9:57 | 9:59
18 | 2026-07-24 | TSG |  | PARMENDRA KUMAR |  | 8:30 | G |  |  | 110022684488 | 10:06 | 10:19 | 10:21 | 10:24
19 | 2026-07-25 | TSG |  | PARMENDRA KUMAR |  | 8:30 | G |  |  | 110022706959 | 9:07 | 9:17 | 9:40 | 9:43
20 | 2026-07-30 | PP |  | BANWARI ORAON |  | 9:00 | G |  |  | 110022796468 | 9:06:00AM | 9:17:00AM | 9:17:00AM | 9:20:00AM
21 | 2026-07-31 | PP | DRIER-1 | ROHIT KUMAR |  | 8:30 | G |  |  | 110022818816 | 8:54:00AM | 9:47:00AM | 9:50:00AM | 10:07:00AM

## XCMG-110T-9206
Infra resources permit delay data MIS
Vendor Name:- Month:-
S. NO. | Date | Department | Location | User Name | Jobs nature SD/N/MSD | Crane reaching time at site | Crane shift reporting time (A/G/B/C shift) | Crane Type |  | Permit No. | PERMIT PROCESS STEPS (Railway time format) | [6 empty] | Actual reason of permit delay
[9 empty] | Hiring cost/ hour |  | A. Permit Create Time (Created by User) | B. PTW requested time (User requested to Operation) | C. Permit Issued time (Operation approved permit) | D. Permit Taken time (Vendor accepted) | Total permit delay time (D-A) | Total permit delay hours | Permit delay cost |  | BD | G | 40T | 1350
1 | 2026-07-01 | LIME PLANT | KLIN#1 | GULAB CHANDRA THAKUR |  | 9:30 | G |  |  | 110022243260 | 10:18:00AM | 10:22 | 10:22 | 10:23:00AM
2 | 2026-07-02 | H-BF | H BF STOVE | ABHISHEK GUPTA |  | 9:30 | G |  |  | 110022251897 | 10:32 | 10:36 | 10:36 | 11:05
3 | 2026-07-04 | MRD |  | SANTOSH PAL |  | 14:30 | B |  |  | 110022303472 | 14:38 | 3:41:00PM | 3:42:00PM | 4:19:00PM
4 | 2026-07-06 | CP-IEM |  | SURAJ BOTHARA |  | 9:30 | G |  |  | 110022321974 | 10:42 | 11:13 | 11:13:00AM | 11:17
5 | 2026-07-07 | FMD | GHB | SAYAN HAZRA |  | 9:00 | G |  |  | 110022353933 | 9:20 | 9:41 | 9:43 | 9:43
6 | 2026-07-08 | FMD | GHB | SAYAN HAZRA |  | 9:00 | G |  |  | 110022374834 | 9:18 | 9:40:00AM | 9:42:00AM | 9:42:00AM
7 | 2026-07-09 | G-BF FME |  | M PRAVEEN |  | 9:30 | G |  |  | 110022405157 | 15:23 | 3:30:00PM | 3:30:00PM | 3:30:00PM
8 | 2026-07-10 | G-BF FME |  | M PRAVEEN |  | 9:00 | G |  |  | 110022425411 | 14:59 | 3:14:00PM | 3:14:00PM | 3:14:00PM
9 | 2026-07-11 | PP |  | PANCHANAN PANDA |  | 9:00 | G |  |  | 110022436419 | 9:14:00AM | 9:43:00AM | 9:55:00AM | 10:06:00AM
10 | 2026-07-13 | H-BF |  | ABHISHEK GUPTA |  | 9:30 | G |  |  | 110022468936 | 10:07:00AM | 10:20:00AM | 10:43:00AM | 10:43:00AM
11 | 2026-07-15 | WMD | CETP | SUBARTA DAS |  | 9:15 | G |  |  | 110022508764 | 9:49 | 10:17:00AM | 10:18:00AM | 10:21:00AM
12 | 2026-07-16 | A-F BF |  | SUNIL SINHA |  | 9:30 | G |  |  | 110022536837 | 11:10:00AM | 11:13:00AM | 11:13:00AM | 11:13:00AM
13 | 2026-07-18 | HSM GATE | HSM GATE | SAROJ RAI |  | 8:00:00AM | G |  |  | 110022567971 | 8:06:00AM | 8:09:00AM | 8:09:00AM | 8:10:00AM
14 | 2026-07-19 | LD-2 | CO GAS SYSTEM | SOUMITRA BID |  | 9:30 | G |  |  | 110022590724 | 10:34:00AM | 11:00:00AM | 11:38:00AM | 11:38:00AM
15 | 2026-07-20 | LD-2 | CO GAS SYSTEM | SOUMITRA BID |  | 9:00:00AM | G |  |  | 110022605810 | 9:33:00AM | 10:09:00AM | 10:09:00AM | 10:09
|  | HSM-FME |  | SUMIT KUMAR |  | 13:00 | G |  |  | 110022607209 | 13:39 | 1:47:00PM | 2:24:00PM | 2:24:00PM
16 | 2026-07-21 | COKE PLANT |  | SUNIL RAY |  | 9:00 | G |  |  | 110022626302 | 9:24:00AM | 10:00:00AM | 10:00 | 10:28:00AM
17 | 2026-07-23 | SPP |  | SAMEER MAHATO |  | 9:30:00AM | G |  |  | 110022668719 | 10:20:00AM | 10:22:00AM | 10:23:00AM | 10:25:00AM
18 | 2026-07-24 | H BF |  | KRISHNAM KUMAR |  | 9:00:00AM | G |  |  | 110022684488 | 9:26:00AM | 10:07:00AM | 10:10:00AM | 10:15:00AM
19 | 2026-07-25 | HSM SECURITY | HSM GATE | SAROJ RAI |  | 6:00 | A |  |  | 110022701667 | 6:47:00AM | 6:49:00AM | 6:49:00AM | 6:49:00AM
20 | 2026-07-27 | BG |  | RAJNISH SINGH |  | 9:30 | G |  |  | 110022741402 | 9:50:00AM | 11:27:00AM | 11:27:00AM | 11:27:00AM
21 | 2026-07-28 | BG |  | RAJNISH SINGH |  | 9:00 | G |  |  | 110022763149 | 10:27 | 10:38:00AM | 10:57:00AM | 10:57:00AM
22 | 2026-07-29 | PH-4 |  | ROHIT PANDIT |  | 9:00 | G |  |  | 110022769096 | 10:05:00AM | 10:34:00AM | 4:06:00PM | 4:07:00PM
23 | 2026-07-30 | PP | BELT GROUP | RAJNISH SINGH |  | 9:00 | G |  |  | 110022800014 | 9:34:00AM | 10:40:00AM | 10:41:00AM | 10:47:00AM
24 | 2026-07-31 | PP | BELT GROUP | RAJNISH SINGH |  | 9:00 | G |  |  | 110022822312 | 11:30:00AM | 11:57:00AM | 11:59:00AM | 12:29

## XCMG-110T-2-9245
Infra resources permit delay data MIS
Vendor Name:- Month:-
S. NO. | Date | Department | Location | User Name | Jobs nature SD/N/MSD | Crane reaching time at site | Crane shift reporting time (A/G/B/C shift) | Crane Type |  | Permit No. | PERMIT PROCESS STEPS (Railway time format) | [6 empty] | Actual reason of permit delay
[9 empty] | Hiring cost/ hour |  | A. Permit Create Time (Created by User) | B. PTW requested time (User requested to Operation) | C. Permit Issued time (Operation approved permit) | D. Permit Taken time (Vendor accepted) | Total permit delay time (D-A) | Total permit delay hours | Permit delay cost |  | BD | G | 40T | 1350
1 | 2026-07-01 | A-F BF |  | SUNIL SINHA |  | 9:30 | G |  |  | 110022250483 | 10:17 | 10:36:00AM | 10:37:00AM | 10:37:00AM
2 | 2026-07-02 | PELLET PLANT | PELLET SCREENING | RIYA |  | 9:30 | G |  |  | 110022262696 | 10:00:00AM | 10:18:00AM | 10:19:00AM | 10:25:00AM
3 | 2026-07-03 | PELLET PLANT | PELLET SCREENING | MUKESH SINGH |  | 6:00 | A |  |  | 110022269643 | 6:21 | 6:41:00AM | 6:41:00AM | 6:45:00AM
4 | 2026-07-04 | PELLET PLANT |  | MUKESH SINGH |  | 9:00:00AM | G |  |  | 110022287370 | 9:08:00AM | 9:21:00AM | 9:22:00AM | 9:54:00AM
5 | 2026-07-07 | RMM |  | SOURAV SHARMA |  | 9:30 | G |  |  | 110022353040 | 15:50 | 4:05:00PM | 4:10:00PM | 4:10:00PM
6 | 2026-07-09 | TSG | SINTER MACHINE ROUTE | PARMENDRA KUMAR |  | 8:30 | G |  |  | 1100224002348 | 13:42 | 13:49 | 1:52:00PM | 13:56
7 | 2026-07-10 | TSG | SINTER MACHINE ROUTE | PARMENDRA KUMAR |  | 8:30 | G |  |  | 110022421966 | 11:49 | 11:53 | 12:01 | 12:02
8 | 2026-07-11 | TSG | SINTER MACHINE ROUTE | PARMENDRA KUMAR |  | 8:30 | G |  |  | 110022443168 | 11:23 | 11:27 | 11:35 | 11:38
9 | 2026-07-12 | TSG | SINTER MACHINE ROUTE | PARMENDRA KUMAR |  | 8:30 | G |  |  | 110022455428 | 9:30 | 9:34 | 9:37:00AM | 9:39:00AM
10 | 2026-07-13 | TSG | SINTER MACHINE ROUTE | PARMENDRA KUMAR |  | 8:30 | G |  |  | 110022474666 | 10:18:00AM | 10:26:00AM | 10:31:00AM | 10:31:00AM
11 | 2026-07-14 | TSG | SINTER MACHINE ROUTE | PARMENDRA KUMAR |  | 8:30 | G |  |  | 110022493853 | 9:35:00AM | 9:44:00AM | 9:49:00AM | 9:50:00AM
12 | 2026-07-15 | TSG | SINTER MACHINE ROUTE | PARMENDRA KUMAR |  | 8:30 | G |  |  | 110022512831 | 9:14:00AM | 9:34:00AM | 9:47:00AM | 9:53:00AM
13 | 2026-07-16 | TSG | SINTER MACHINE ROUTE | PARMENDRA KUMAR |  | 8:30 | G |  |  | 110022534449 | 9:38:00AM | 9:54:00AM | 9:56:00AM | 10:00:00AM
14 | 2026-07-17 | TSG | SINTER MACHINE ROUTE | PARMENDRA KUMAR |  | 8:30 | G |  |  | 110022553638 | 9:43:00AM | 10:01:00AM | 10:04:00AM | 10:05:00AM
15 | 2026-07-18 | TSG | SINTER MACHINE ROUTE | PARMENDRA KUMAR |  | 8:30 | G |  |  | 110022574520 | 9:54:00AM | 10:03:00AM | 10:16:00AM | 10:18:00AM
16 | 2026-07-19 | TSG | SINTER MACHINE ROUTE | PARMENDRA KUMAR |  | 8:30 | G |  |  | 110022589750 | 9:43:00AM | 10:03:00AM | 10:04:00AM | 10:06:00AM
17 | 2026-07-20 | TSG | COKE PLANT BATTERY MACHINE | PARMENDRA KUMAR |  | 8:30 | G |  |  | 110022608932 | 10:34:00AM | 10:45:00AM | 10:47:00AM | 11:16:00AM
18 | 2026-07-21 | TSG | SINTER MACHINE ROUTE | PARMENDRA KUMAR |  | 8:30 | G |  |  | 110022629310 | 10:28:00AM | 10:34:00AM | 10:37:00AM | 10:38:00AM
19 | 2026-07-22 | TSG | SINTER MACHINE ROUTE | PARMENDRA KUMAR |  | 8:30 | G |  |  | 110022649704 | 10:14:00AM | 10:26:00AM | 10:27:00AM | 10:27:00AM
20 | 2026-07-23 | TSG | BF-2 | PARMENDRA KUMAR |  | 8:30 | G |  |  | 110022669428 | 9:53:00AM | 11:03:00AM | 11:03:00AM | 11:03:00AM
21 | 2026-07-24 | TSG | BF-2 | PARMENDRA KUMAR |  | 8:30 | G |  |  | 110022690142 | 9:55:00AM | 10:12:00AM | 10:13:00AM | 10:13:00AM
22 | 2026-07-25 | TSG | BF-2 | PARMENDRA KUMAR |  | 8:30 | G |  |  | 110022711665 | 10:51:00AM | 11:05:00AM | 11:06:00AM | 11:06:00AM
23 | 2026-07-26 | TSG | BF-2 | PARMENDRA KUMAR |  | 8:30 | G |  |  | 110022725800 | 1:29:00PM | 2:14:00PM | 2:15:00PM | 2:15:00PM
24 | 2026-07-30 | PELLET PLANT | DRIER-1 | ROHIT KUMAR |  | 9:15 | G |  |  | 110022796484 | 9:18:00AM | 9:31:00AM | 9:32:00AM | 9:37:00AM
25 | 2026-07-31 | PELLET PLANT | DRIER-2 | ROHIT KUMAR |  | 8:30 | G |  |  | 110022818818 | 8:55:00AM | 9:47:00AM | 9:50:00AM | 10:06:00AM

## SANY-160 T
Infra resources permit delay data MIS
Vendor Name:- Month:-
S. NO. | Date | Department | Location | User Name | Jobs nature SD/N/MSD | Crane reaching time at site | Crane shift reporting time (A/G/B/C shift) | Crane Type |  | Permit No. | PERMIT PROCESS STEPS (Railway time format) | [6 empty] | Actual reason of permit delay
[9 empty] | Hiring cost/ hour |  | A. Permit Create Time (Created by User) | B. PTW requested time (User requested to Operation) | C. Permit Issued time (Operation approved permit) | D. Permit Taken time (Vendor accepted) | Total permit delay time (D-A) | Total permit delay hours | Permit delay cost |  | BD | G | 40T | 1350
1 | 2026-07-01 | FBF | F-BF BFS | ABHISHEK SHARMA |  | 9:30 | G |  |  | 110022250443 | 10:16 | 10:27 | 10:27 | 10:29:00AM
2 | 2026-07-03 | FBF | F-BF BFS | ABHISHEK SHARMA |  | 6:00:00AM | A |  |  | 110022287637 | 9:15 | 9:35:00AM | 10:08:00AM | 10:10:00AM
3 | 2026-07-04 | FBF | F-BF BFS | ABHISHEK SHARMA |  | 8:30:00AM | G |  |  | 110022317037 | 10:48:00PM | 11:15:00PM | 11:15:00PM | 11:17:00PM
4 | 2026-07-05 | FBF | F-BF BFS | ABHISHEK SHARMA |  | 8:30:00AM | G |  |  | 110022323010 | 10:05:00AM | 10:39:00AM | 11:38:00AM | 11:42:00AM
5 | 2026-07-06 | FBF | F-BF BFS | ABHISHEK SHARMA |  | 8:30:00AM | G |  |  | 110022337202 | 9:21:00AM | 9:35:00AM | 10:31:00AM | 10:36:00AM
6 | 2026-07-07 | FBF | F-BF BFS | ABHISHEK SHARMA |  | 8:00:00AM | G |  |  | 110022352336 | 8:05:00AM | 8:19:00AM | 8:26:00AM | 8:41:00AM
7 | 2026-07-10 | MRD | LONG TOM YARD | SANTOSH PAL |  | 9:30:00AM | G |  |  | 110022420272 | 10:04:00AM | 10:13:00AM | 10:13:00AM | 10:13:00AM
8 | 2026-07-13 | COKE PLANT | BOOSTER AREA | JAYANAND KUMAR |  | 8:30 | G |  |  | 110022469457 | 8:48:00AM | 9:07:00AM | 9:13:00AM | 9:13:00AM
9 | 2026-07-14 | BELT GROUP | SP-1 | SOURAV PANDEY |  | 9:30:00AM | G |  |  | 110022497532 | 12:30:00PM | 3:08:00PM | 3:22:00PM | 3:25:00PM
10 | 2026-07-15 | FMD | GHB | R.K PRASAD |  | 9:00:00AM | G |  |  | 110022488674 | 9:05:00AM | 9:26:00AM | 9:27:00AM | 10:19:00AM
11 | 2026-07-16 | FMD | GHB | R.K PRASAD |  | 9:00:00AM | G |  |  | 110022529637 | 9:36:00AM | 9:36:00AM | 9:45:00AM | 9:58:00AM
12 | 2026-07-17 | FMD | GHB | R.K PRASAD |  | 9:00:00AM | G |  |  | 110022540996 | 9:44:00AM | 10:28:00AM | 10:29:00AM | 10:32:00AM
|  | NBM | DCW SYSTEM | J SOREN |  | 12:00 | G |  |  | 110022556873 | 12:16:00PM | 12:30:00PM | 12:30:00PM | 12:31:00PM
13 | 2026-07-18 | NBM | DCW SYSTEM | J SOREN |  | 8:00:00AM | G |  |  | 110022567998 | 8:08 | 8:25:00AM | 8:25:00AM | 8:26:00AM
14 | 2026-07-21 | COKE PLANT | BATTERY#8 | KAMLESH KUMAR |  | 9:30 | G |  |  | 110022627246 | 9:38 | 10:17:00AM | 10:21:00AM | 10:24:00AM
15 | 2026-07-22 | COKE PLANT | BPP | KAMLESH KUMAR |  | 8:30:00AM | G |  |  | 110022646626 | 9:21:00AM | 9:26:00AM | 9:26:00AM | 9:26:00AM
16 | 2026-07-23 | COKE PLANT | BPP | JAYANAND KUMAR |  | 8:30:00AM | G |  |  | 110022664830 | 8:52:00AM | 9:03:00AM | 9:11:00AM | 9:12:00AM
17 | 2026-07-24 | COKE PLANT | BPP | JAYANAND KUMAR |  | 8:30:00AM | G |  |  | 110022684652 | 8:45 | 8:50:00AM | 8:57:00AM | 9:18:00AM
18 | 2026-07-25 | COKE PLANT | BPP | JAYANAND KUMAR |  | 8:30:00AM | G |  |  | 110022704723 | 8:36 | 8:53 | 9:00 | 9:03
19 | 2026-07-27 | COKE PLANT | BATTERY#10,11 | SANJAY MISHRA |  | 8:30 | G |  |  | 110022738461 | 9:01:00AM | 9:09:00AM | 9:14:00AM | 9:45:00AM
20 | 2026-07-28 | C BF | BFS | SUNIL SHIRWAR |  | 9:30 | G |  |  | 110022762378 | 10:02 | 10:38:00AM | 10:38:00AM | 10:58:00AM
21 | 2026-07-29 | E-BF | BFS | SUNIL SHIRWAR |  | 8:30 | G |  |  | 110022777469 | 8:48:00AM | 9:33:00AM | 9:33:00AM | 9:33:00AM
22 | 2026-07-30 | PELLET PLANT | PGS BELLOW | ROHIT KUMAR |  | 9:15:00AM | G |  |  | 110022796872 | 9:30:00AM | 9:49:00AM | 9:49:00AM | 9:54:00AM
23 | 2026-07-31 | PELLET PLANT | PGS BELLOW | ROHIT KUMAR |  | 8:30:00AM | G |  |  | 110022816983 | 9:49 | 10:31:00AM | 11:23:00AM | 11:26:00AM

## XCMG-350 T-1
Infra resources permit delay data MIS
Vendor Name:- Month:-
S. NO. | Date | Department | Location | User Name | Jobs nature SD/N/MSD | Crane reaching time at site | Crane shift reporting time (A/G/B/C shift) | Crane Type |  | Permit No. | PERMIT PROCESS STEPS (Railway time format) | [6 empty] | Actual reason of permit delay
[9 empty] | Hiring cost/ hour |  | A. Permit Create Time (Created by User) | B. PTW requested time (User requested to Operation) | C. Permit Issued time (Operation approved permit) | D. Permit Taken time (Vendor accepted) | Total permit delay time (D-A) | Total permit delay hours | Permit delay cost |  | BD | G | 40T | 1350
1 | 2026-07-01 | PP | GREEN PELLETIZING BUILDING | BASHRATHUL ISLAM |  | 8:30 | G |  |  | 110022235592 | 9:05 | 9:44 | 9:45 | 9:45
2 | 2026-07-03 | HSM | CIRCULATING PUMP HOUSE | ADITYA ANAND |  | 6:00:00AM | A |  |  | 110022280722 | 6:22:00AM | 8:51:00AM | 8:51:00AM | 8:51:00AM
3 | 2026-07-04 | GBF | SGP | MANOJ KUMAR |  | 14:30 | G |  |  | 110022306354 | 15:35 | 3:36:00PM | 3:36:00PM | 3:36:00PM
4 | 2026-07-07 | FMD | GHB | NIKITA KUMARI |  | 10:30 | G |  |  | 110022358511 | 10:43:00AM | 10:47:00AM | 10:48:00AM | 10:50:00AM
5 | 2026-07-08 | FMD | GHB | SAYAN HAZRA |  | 9:00 | G |  |  | 110022374836 | 9:19:00AM | 9:21:00AM | 9:24:00AM | 9:25:00AM
6 | 2026-07-09 | SP-3 | PROCESS GAS SYSTEM | SUJOY MUKHERJEE |  | 9:30 | G |  |  | 110022400233 | 10:18:00AM | 11:13:00AM | 11:18:00AM | 11:23:00AM
7 | 2026-07-10 | SP-3 | PROCESS GAS SYSTEM | SUJOY MUKHERJEE |  | 9:00 | G |  |  | 110022417280 | 9:18:00AM | 9:46:00AM | 9:47:00AM | 10:20:00AM
8 | 2026-07-11 | RMBB-2 | BARREL AREA | SURENDRA KUMAR |  | 9:00:00AM | G |  |  | 110022439171 | 9:22:00AM | 9:30:00AM | 10:16:00AM | 10:18:00AM
9 | 2026-07-13 | RMBB-2 | BARREL AREA | SURENDRA KUMAR |  | 9:00:00AM | G |  |  | 110022471667 | 9:21:00AM | 9:46:00AM | 10:06:00AM | 10:07:00AM
10 | 2026-07-14 | RMBB-2 | BARREL AREA | SURENDRA KUMAR |  | 8:30 | G |  |  | 110022490220 | 8:46:00AM | 8:59:00AM | 9:03:00AM | 9:09:00AM
11 | 2026-07-15 | RMBB-2 | BARREL AREA | SURENDRA KUMAR |  | 8:30 | G |  |  | 110022510210 | 8:40:00AM | 8:49:00AM | 8:54:00AM | 9:20:00AM
12 | 2026-07-16 | RMBB-2 | BARREL AREA | SURENDRA KUMAR |  | 8:30 | G |  |  | 110022530926 | 8:40:00AM | 8:51:00AM | 8:54:00AM | 9:07:00AM
13 | 2026-07-17 | RMBB-2 | BARREL AREA | SURENDRA KUMAR |  | 8:30 | G |  |  | 110022553402 | 9:39:00AM | 9:44:00AM | 9:46:00AM | 9:50:00AM
14 | 2026-07-18 | RMBB-2 | BARREL AREA | SURENDRA KUMAR |  | 8:30 | G |  |  | 110022570798 | 8:57 | 9:22:00AM | 9:40:00AM | 9:48:00AM
15 | 2026-07-19 | COKE PLANT | NEW BPP | SHAHSIKANT KUMAR |  | 8:30 | G |  |  | 110022588236 | 8:50:00AM | 8:55:00AM | 8:58:00AM | 8:58:00AM
16 | 2026-07-20 | SP-1 | GARDEN AREA | SURENDRA KUMAR |  | 9:30 | G |  |  | 110022608526 | 10:18:00AM | 10:53:00AM | 11:12:00AM | 11:13:00AM
17 | 2026-07-21 | SP-1 | GARDEN AREA | SURENDRA KUMAR |  | 8:30 | G |  |  | 110022627587 | 9:44:00AM | 10:40:00AM | 10:41:00AM | 10:45:00AM
18 | 2026-07-22 | SP-1 | GARDEN AREA | SURENDRA KUMAR |  | 8:30 | G |  |  | 110022644344 | 8:47:00AM | 9:21:00AM | 9:55:00AM | 9:57:00AM
19 | 2026-07-23 | SP-1 | GARDEN AREA | SURENDRA KUMAR |  | 8:30 | G |  |  | 110022664549 | 8:48:00AM | 9:11:00AM | 9:13:00AM | 9:18:00AM
20 | 2026-07-24 | SP-4 | BG | SAURABH PANDEY |  | 9:30 | G |  |  | 110022690849 | 10:13:00AM | 10:39:00AM | 10:59:00AM | 11:03:00AM
21 | 2026-07-27 | SP-1 | GARDEN AREA | SURENDRA KUMAR |  | 6:00 | A |  |  | 110022733528 | 6:28:00AM | 6:52:00AM | 7:01:00AM | 7:02:00AM
22 | 2026-07-29 | SP-1 | GARDEN AREA | SURENDRA KUMAR |  | 6:00 | A |  |  | 110022772891 | 6:21:00AM | 6:49:00AM | 7:13:00AM | 7:14:00AM
23 | 2026-07-30 | SP-1 | GARDEN AREA | SURENDRA KUMAR |  | 8:30 | G |  |  | 110022799850 | 9:07:00AM | 9:53:00AM | 10:04:00AM | 10:08:00AM
24 | 2026-07-31 | SP-1 | GARDEN AREA | SURENDRA KUMAR |  | 8:30 | G |  |  | 110022820426 | 8:55:00AM | 9:16:00AM | 9:18:00AM | 9:19:00AM

## XCMG-350 T-2
Infra resources permit delay data MIS
Vendor Name:- Month:-
S. NO. | Date | Department | Location | User Name | Jobs nature SD/N/MSD | Crane reaching time at site | Crane shift reporting time (A/G/B/C shift) | Crane Type |  | Permit No. | PERMIT PROCESS STEPS (Railway time format) | [6 empty] | Actual reason of permit delay
[9 empty] | Hiring cost/ hour |  | A. Permit Create Time (Created by User) | B. PTW requested time (User requested to Operation) | C. Permit Issued time (Operation approved permit) | D. Permit Taken time (Vendor accepted) | Total permit delay time (D-A) | Total permit delay hours | Permit delay cost |  | BD | G | 40T | 1350
1 | 2026-07-04 | SP-2 |  | D.MAWAL |  | 8:30:00AM | G |  |  | 110022309166 | 10:12:00AM | 10:25:00AM | 10:26:00AM | 10:27:00AM
2 | 2026-07-05 | SP-2 |  | SUJOY MUKHERJEE |  | 8:30:00AM | G |  |  | 110022323611 | 11:22:00AM | 11:28:00AM | 11:28:00AM | 11:28:00AM
3 | 2026-07-06 | SP-2 |  | SUJOY MUKHERJEE |  | 8:30:00AM | G |  |  | 110022339397 | 10:02:00AM | 10:06:00AM | 10:06:00AM | 10:06:00AM
4 | 2026-07-09 | G BF |  | AMARJIT RAY |  | 9:00:00AM | G |  |  | 110022395826 | 10:10:00AM | 10:15:00AM | 10:15:00AM | 10:39:00AM
5 | 2026-07-10 | G BF |  | AMARJIT RAY |  | 9:00:00AM | G |  |  | 110022414145 | 10:01:00AM | 10:05:00AM | 10:05:00AM | 10:35:00AM
6 | 2026-07-11 | COKE PLANT | BPP | VIKASH ANAND |  | 9:00:00AM | G |  |  | 110022437489 | 9:02:00AM | 9:06:00AM | 9:25:00AM | 9:26:00AM
7 | 2026-07-13 | PELLET PLANT | BELT GROUP | 9031053673 |  | 9:30:00AM | G |  |  | 110022471917 | 10:37:00AM | 10:42:00AM | 10:42:00AM | 10:46:00AM
8 | 2026-07-15 | HSM-FME | HSM HT POWER | SIDDHARTH SHANKAR |  | 9:30:00AM | G |  |  | 110022516690 | 10:36:00AM | 12:01:00PM | 12:01:00PM | 12:02:00PM
9 | 2026-07-16 | HSM-FME | HSM HT POWER | SIDDHARTH SHANKAR |  | 8:30:00AM | G |  |  | 110022531991 | 8:51:00AM | 9:00:00AM | 9:00:00AM | 9:00:00AM
10 | 2026-07-17 | HSM-FME | HSM HT POWER | SIDDHARTH SHANKAR |  | 8:30:00AM | G |  |  | 110022554307 | 9:54:00AM | 9:59:00AM | 9:59:00AM | 10:01:00AM
|  | FMD | GHB | R.K PRASAD |  | 2:00:00PM | G |  |  | 110022542693 | 2:07:00PM | 2:27:00PM | 2:27:00PM | 2:27:00PM
11 | 2026-07-18 | FMD | GHB | R.K PRASAD |  | 8:30:00AM | G |  |  | 110022566062 | 8:50:00AM | 9:26:00AM | 9:26:00AM | 10:13:00AM
12 | 2026-07-19 | FMD | GHB | R.K PRASAD |  | 8:30:00AM | G |  |  | 110022580684 | 9:27:00AM | 9:42:00AM | 9:45:00AM | 9:53:00AM
13 | 2026-07-20 | FMD | GHB | R.K PRASAD |  | 8:30:00AM | G |  |  | 110022603108 | 9:05:00AM | 9:24:00AM | 9:25:00AM | 9:37:00AM
14 | 2026-07-21 | FMD | GHB | R.K PRASAD |  | 8:30:00AM | G |  |  | 110022623506 | 9:12:00AM | 9:21:00AM | 9:22:00AM | 9:25:00AM
15 | 2026-07-22 | FMD | GHB | R.K PRASAD |  | 8:30:00AM | G |  |  | 110022642743 | 9:35:00AM | 9:41:00AM | 9:41:00AM | 9:42:00AM
16 | 2026-07-24 | SP-1 | GARDEN AREA | SURENDRA KUMAR |  | 8:30:00AM | G |  |  | 110022686332 | 8:55:00AM | 10:03:00AM | 10:13:00AM | 10:28:00AM
17 | 2026-07-25 | SP-1 | GARDEN AREA | SURENDRA KUMAR |  | 8:30:00AM | G |  |  | 110022705607 | 8:49:00AM | 9:18:00AM | 9:38:00AM | 9:39:00AM
18 | 2026-07-26 | SP-1 | GARDEN AREA | SURENDRA KUMAR |  | 6:00:00AM | A |  |  | 110022719590 | 6:08:00AM | 7:00:00AM | 7:04:00AM | 7:05:00AM
19 | 2026-07-27 | SPP |  | RATAN LAL |  | 9:30:00AM | G |  |  | 110022736834 | 9:38:00AM | 10:06:00AM | 10:12:00AM | 10:12:00AM
20 | 2026-07-28 | SP-1 | GARDEN AREA | SURENDRA KUMAR |  | 6:00:00AM | A |  |  | 110022753685 | 6:35:00AM | 6:49:00AM | 6:49:00AM | 6:52:00AM
21 | 2026-07-30 | PP | BELT GROUP SILO | BASHRATHUL ISLAM |  | 8:30:00AM | G |  |  | 110022779354 | 8:50:00AM | 9:42:00AM | 9:42:00AM | 9:46:00AM
22 | 2026-07-31 | PP | BELT GROUP SILO | BASHRATHUL ISLAM |  | 8:30:00AM | G |  |  | 110022820043 | 9:30:00AM | 9:58:00AM | 9:59:00AM | 10:00:00AM

## SANY-450 T
Infra resources permit delay data MIS
Vendor Name:- Month:- |  | IHPL | MONTH-JULY-2026
S. NO. | Date | Department | Location | User Name | Jobs nature SD/N/MSD | Crane reaching time at site | Crane shift reporting time (A/G/B/C shift) | Crane Type |  | Permit No. | PERMIT PROCESS STEPS (Railway time format) | [6 empty] | Actual reason of permit delay
[9 empty] | Hiring cost/ hour |  | A. Permit Create Time (Created by User) | B. PTW requested time (User requested to Operation) | C. Permit Issued time (Operation approved permit) | D. Permit Taken time (Vendor accepted) | Total permit delay time (D-A) | Total permit delay hours | Permit delay cost |  | BD | G | 40T | 1350
1 | 2026-07-01 | TSG | DRI-2 PLANT | KAMAL DEEP SINGH |  | 8:30:00AM | G |  |  | 110022255885 | 5:37:00PM | 5:42:00PM | 5:43:00PM | 5:43:00PM
2 | 2026-07-02 | TSG | DRI-2 PLANT | KAMAL DEEP SINGH |  | 8:30:00AM | G |  |  | 110022266154 | 9:01:00AM | 9:22:00AM | 9:22:00AM | 9:27:00AM
3 | 2026-07-03 | TSG | DRI-2 PLANT | KAMAL DEEP SINGH |  | 8:30:00AM | G |  |  | 110022286207 | 8:46 | 8:52:00AM | 8:52:00AM | 8:52:00AM
4 | 2026-07-04 | TSG | DRI-2 PLANT | KAMAL DEEP SINGH |  | 8:30:00AM | G |  |  | 110022308247 | 9:51 | 9:56:00AM | 10:01:00AM | 10:00:00AM
5 | 2026-07-05 | C/W | CRANE VENDOR PARK | SUMAN BHAATACHARYA |  | 8:30:00AM | G |  |  | 110022321402 | 8:58 | 9:13:00AM | 9:13:00AM | 9:13:00AM
6 | 2026-07-10 | FMD | GLM | SHLOK VERMA |  | 9:00:00AM | G |  |  | 110022414661 | 9:13:00AM | 1:47:00PM | 1:48:00PM | 1:49:00PM
7 | 2026-07-11 | HSM | CIRCULATING PUMP HOUSE | ADITYA ANAND SINGH |  | 8:30 | G |  |  | 110022437150 | 8:58:00AM | 9:06:00AM | 9:06:00AM | 9:06:00AM
8 | 2026-07-13 | EQMS | SYMS | ASHISH MOHAPATRA |  | 9:00:00AM | G |  |  | 110022472704 | 9:36:00AM | 10:03:00AM | 2:45:00PM | 14:45
9 | 2026-07-14 | EQMS | SYMS | ASHISH MOHAPATRA |  | 8:30 | G |  |  | 110022490549 | 8:51:00AM | 9:09:00AM | 10:36:00AM | 10:42:00AM
10 | 2026-07-15 | FMD | GHB | R.K PRASAD |  | 9:00:00AM | G |  |  | 110022488679 | 9:26:00AM | 10:48:00AM | 10:48:00AM | 11:14:00AM
11 | 2026-07-16 | FMD | GHB | R.K PRASAD |  | 8:30 | G |  |  | 110022529638 | 9:41:00AM | 9:44:00AM | 9:44:00AM | 9:50:00AM
12 | 2026-07-17 | FMD | GHB | R.K PRASAD |  | 8:30 | G |  |  | 110022540998 | 9:46:00AM | 10:30:00AM | 10:31:00AM | 10:32:00AM
13 | 2026-07-18 | FMD | GHB | R.K PRASAD |  | 8:30 | G |  |  | 110022566058 | 8:47:00AM | 9:25:00AM | 2:23:00PM | 2:45:00PM
14 | 2026-07-19 | FMD | GHB | R.K PRASAD |  | 20:00 | N |  |  | 110022587611 | 8:25:00PM | 8:25:00PM | 8:25:00PM | 8:25:00PM
15 | 2026-07-20 | FMD | GHB | R.K PRASAD |  | 8:30:00AM | G |  |  | 110022603105 | 9:04:00AM | 9:17:00AM | 9:18:00AM | 9:37:00AM
16 | 2026-07-21 | FMD | GHB | R.K PRASAD |  | 8:30:00AM | G |  |  | 110022623508 | 9:13:00AM | 9:20:00AM | 9:21:00AM | 9:28
17 | 2026-07-22 | GBF | GBF OFFICE | SUMIT RANJAN |  | 9:30:00AM | G |  |  | 110022648690 | 9:49:00AM | 3:09:00PM | 3:09:00PM | 3:10:00PM
18 | 2026-07-23 | GBF | GBF OFFICE | SUMIT RANJAN |  | 8:30:00AM | G |  |  | 110022665075 | 8:56:00AM | 9:08:00AM | 9:13:00AM | 9:17:00AM
19 | 2026-07-28 | FMD | GCP-2 | KADMA RAGHU |  | 9:00:00AM | G |  |  | 110022757439 | 9:07:00AM | 9:10:00AM | 9:11 | 10:22:00AM
20 | 2026-07-30 | FMD | GCP-2 (CRANE REMOVAL) | KADMA RAGHU |  | 9:00:00AM | G |  |  | 110022795493 | 9:09:00AM | 9:24:00AM | 9:25:00AM | 9:36:00AM

## Sheet4 (hidden)
A-F BF | 86951.9444
RMM | 40738.7674
CRM | 32594.375
PP | 26699.8264
HSM | 21792.6042
LD#2 | 21263.2292
RMBB1 | 18944.0625
OLD CP | 16679.5139
GBF | 16461.0417
BPH | 11513.9063
NEW CP | 10734.5486